## Security Findings
ID | Title | Category | Severity | File & Line Number | Exploit Scenario | Recommended Fix | Status | Verification Notes
BUG-001 | Default admin access code still active in production (self-elevation to admin) | Configuration & Secrets / Access Control | Critical | supabase/phase14_admin_access.sql:97-99 (default code 'CHANGE-ME-ADMIN-2026'); app/login/actions.ts (adminSignup) | The admin gate is a single secret code stored in app_secrets. The default value 'CHANGE-ME-ADMIN-2026' is committed to the PUBLIC GitHub repo and was never rotated on the live deployment. VERIFIED LIVE: rpc/verify_admin_code with the default code returns true. Any anonymous person can open /admin-access, sign up with that code, then redeem_admin_access() elevates their own profile to role='admin' — granting full admin: read/modify all members, change roles, delete content, post announcements. Existing users can also call the redeem RPC directly. | 1) Immediately rotate the code: UPDATE app_secrets SET value='<long-random>' WHERE key='admin_access_code'. 2) Remove the default literal from the SQL file / git history. 3) Audit profiles for role='admin' rows you didn't create and demote them. 4) Longer term, replace a shared static code with per-invite tokens (single-use, expiring) and rate-limit verify_admin_code. | Fixed | Repo: phase14_admin_access.sql now seeds a random 128-bit code (gen_random_uuid x2) instead of a known default. Live: owner rotated app_secrets.admin_access_code to a high-entropy value. VERIFIED LIVE 2026-07-06: verify_admin_code('CHANGE-ME-ADMIN-2026') now returns false (was true); new code returns true; wrong code false. Regression: normal scholar/alumni signup path unchanged; existing admins (only 'Admin test' + 'layla nasser', no rogue accounts) unaffected.
BUG-002 | Unauthenticated exposure of all member PII (email, name, country, role) via public REST API | Access Control / Data Protection | High | supabase/setup_profiles_auth.sql:36-37 (profiles_select policy) | The profiles_select RLS policy is 'USING (auth.uid() = id OR profile_visibility = 'public')' with no 'TO authenticated' restriction, and the default visibility is public. The Supabase URL + anon key are public (embedded in client JS). VERIFIED LIVE: a single curl to /rest/v1/profiles with just the anon key returns every member's full_name, email, country and role — including which accounts are admins. Enables mass email harvesting, targeted phishing of admins, and account enumeration with no login. | Restrict directory reads to logged-in users: change the policy to 'FOR SELECT TO authenticated USING (...)'. Stop selecting email in any directory/listing query; expose email only to the profile owner (and admins) via a dedicated column-scoped view or RPC. Consider making profile_visibility default to members-only. | Fixed | Repo: setup_profiles_auth.sql profiles_select now 'to authenticated'; migration supabase/security_hardening.sql. Live: owner applied. VERIFIED LIVE 2026-07-06: anon GET /rest/v1/profiles now returns [] (was dumping every full_name+email+role). Regression: member directory + profile pages still load in-app for logged-in users (owner confirmed).
BUG-003 | Unauthenticated exposure of academic records, employment & skills of all members | Access Control / Data Protection | High | supabase/setup_profiles_auth.sql:47-56 (can_view_profile); setup_profiles_auth.sql:63-78; supabase/phase1_writes.sql:184-185 (alumni_details_select) | can_view_profile() returns true whenever profile_visibility='public', with no requirement that the caller be authenticated, and it gates scholar_academic_records, profile_skills, profile_languages, profile_interests and alumni_details. VERIFIED LIVE: anonymous curl to /rest/v1/scholar_academic_records and /rest/v1/alumni_details returns institutions, GPAs, employers, positions and LinkedIn URLs for public profiles. Sensitive educational/career PII is exposed to the entire internet. | Add 'TO authenticated' to these policies (and to can_view_profile's usage) so only logged-in members can read them. Re-evaluate whether GPA/academic detail should be visible to all members at all, or only to the owner/admins. | Fixed | Repo: can_view_profile() now requires auth.uid() is not null; sar/skills/languages/interests/alumni_details select policies set 'to authenticated'. Live: applied via security_hardening.sql. VERIFIED LIVE 2026-07-06: anon reads of scholar_academic_records, alumni_details, profile_skills, profile_interests all return [] (were leaking GPA/institution/employer/LinkedIn). Regression: authenticated profile pages with skills+academic records still render (owner confirmed).
BUG-004 | Admin access code is brute-forceable (anon RPC, no rate limiting, boolean oracle) | API & Client-Server Trust / Access Control | Medium | supabase/phase14_admin_access.sql:41 (grant verify_admin_code to anon) | verify_admin_code(text) is granted to anon and returns a clean true/false with no throttling or lockout. VERIFIED LIVE: 8 rapid guesses all returned HTTP 200. An attacker can script unlimited guesses against the admin code from the public REST endpoint. Even after BUG-001 is fixed, a weak/guessable code can be cracked offline-style. Combined with redeem_admin_access this yields admin takeover. | Use a high-entropy code (>=128 bits). Do not expose a verify oracle to anon — verify only inside the authenticated redeem path, and add rate limiting / attempt logging (e.g. Supabase edge function with per-IP throttle, or a counter table with lockout). Prefer single-use expiring invite tokens over a static shared code. | Fixed | Repo: phase14_admin_access.sql revokes EXECUTE on verify_admin_code from public/anon/authenticated; app/login/actions.ts adminSignup no longer pre-calls the oracle (redeem_admin_access validates internally). Live: applied via security_hardening.sql. VERIFIED LIVE 2026-07-06: anon rpc/verify_admin_code now returns HTTP 401 'permission denied for function' instead of a boolean. Also mitigated by 144-bit code from BUG-001. Admin creation path unchanged for a correct code (tsc passes).
BUG-005 | Missing HTTP security headers (CSP, X-Frame-Options, X-Content-Type-Options, Referrer-Policy, Permissions-Policy) | Configuration & Secrets | Medium | tbhf-platform/next.config.ts (no headers() block); verified against live response headers | VERIFIED LIVE: responses from the Vercel deployment include only HSTS. There is no Content-Security-Policy (weakens XSS containment, e.g. BUG-006), no X-Frame-Options/frame-ancestors (the app can be iframed -> clickjacking of authenticated actions), no X-Content-Type-Options: nosniff (MIME sniffing), and no Referrer-Policy/Permissions-Policy. | Add an async headers() function in next.config.ts returning: Content-Security-Policy (default-src 'self' plus the Supabase origin for connect/img), X-Frame-Options: DENY (or CSP frame-ancestors 'none'), X-Content-Type-Options: nosniff, Referrer-Policy: strict-origin-when-cross-origin, Permissions-Policy locking down camera/mic/geolocation. Test all pages still load, incl. Supabase image/storage URLs and auth XHR. | Fixed | next.config.ts now sends CSP, X-Frame-Options: DENY, X-Content-Type-Options: nosniff, Referrer-Policy, Permissions-Policy, HSTS; poweredByHeader disabled. CSP scoped to app needs (Supabase https+wss, inline styles, data/blob img, blob workers for pdfjs); 'unsafe-eval' dev-only, prod strict. VERIFIED (dev server :3000, 2026-07-06): all 6 headers present on /:path*, X-Powered-By gone, /login renders 200 (16KB). tsc passes. Recommend re-checking live headers after next Vercel deploy.
BUG-006 | Stored/DOM XSS via unvalidated user-supplied URLs (javascript: scheme) in href | Input Validation & Injection | Medium | components/ProfileView.tsx:257 (linkedin_url); app/(app)/showcase/[id]/page.tsx:80 (external_url/media_url); app/(app)/research/[id]/page.tsx:70 (link_url); components/OpportunityActions.tsx:56 (application link) | User/alumni/admin-supplied URLs (linkedin_url, showcase external_url, research link_url, opportunity application link) are stored without scheme validation (e.g. upsert_my_alumni_details stores linkedin_url verbatim) and rendered directly as <a href={...}>. An attacker can set the value to 'javascript:fetch(...)' or 'javascript:...'; when another member (or an admin reviewing content) clicks the link, script runs in their session -> session/data theft, and if an admin clicks, actions run with admin rights. | Validate/normalize URLs on write and render: allow only http(s):// (and mailto: where relevant); reject or neutralize javascript:, data:, vbscript:. Add a shared safeUrl() helper used at every href sink. React escapes text but does NOT block javascript: URLs. | Fixed | Added lib/safeUrl.ts (allowlists http/https/mailto/tel + relative; blocks javascript:/data:/vbscript: incl. tab/newline/case obfuscation) and applied it to all 10 user-URL href sinks: OpportunityActions, ProfileView, AlumniNetwork, EventsCalendar (x2), ContentModeration, research/[id] (x2), resources, showcase/[id]. VERIFIED 2026-07-06: node unit test 13/13 pass (javascript variants -> undefined/dead link; legit URLs pass through). tsc passes. Regression: legitimate http(s)/mailto/relative links unaffected.
BUG-007 | All Supabase Storage buckets are public — members-only files world-readable by URL | Data Protection / Access Control | Medium | supabase/phase3_resources.sql:81-82 (resources); phase9_research.sql:77-78 (research); phase6_stories.sql:121-122; phase7_showcase.sql:48-49; phase8_events.sql:93-94; phase10_volunteer.sql:110-111; phase30_community_media.sql:21-22; phase1_writes.sql:188-189 (avatars) | Every bucket is created with public=true, including 'resources' and 'research' which hold member-contributed / library documents likely intended for logged-in members only. Public buckets serve any object to anyone who has (or guesses) the object URL, with no auth check — bypassing the app's login gate. Uploaded PII or gated learning material can leak. | For buckets holding non-public content (resources, research, and review-gated uploads), set public=false and serve via signed URLs (createSignedUrl) or an authenticated read policy. Keep only genuinely public assets (e.g. avatars) public. Add upload content-type/size limits. | Open (risk-accepted) | DECISION 2026-07-06: full private-bucket + signed-URL refactor deferred (cross-cutting change to upload/render + data migration; not E2E-verifiable without prod risk). Residual risk reduced: URL-bearing DB rows are now authenticated-only (BUG-002/003), so file URLs are no longer exposed to anon. MITIGATION applied in security_hardening.sql (re-run to apply): file_size_limit + MIME allowlist on resources/research (25MB, docs+images), image-only 10MB on avatars/story-covers/event-posters/projects, 100MB size cap on showcase/community-media. FOLLOW-UP PLAN to fully close: (1) store object PATH not public URL in file_url/media_url; (2) createSignedUrl(path, ttl) at render server-side; (3) migrate existing rows path<-parse(url); (4) alter buckets set public=false for resources+research; (5) test upload+open in-app.
BUG-008 | Vulnerable dependency: postcss < 8.5.10 (XSS) pulled via Next.js | Dependencies | Medium | tbhf-platform/package.json (next 16.2.9 -> postcss); npm audit | npm audit reports 2 moderate vulnerabilities: postcss <8.5.10 has an XSS via unescaped </style> in CSS stringify output (GHSA-qx2v-qp2m-jg93), reachable transitively through Next.js. Low direct impact for this app's usage but should be patched to stay clean. | Run 'npm audit' regularly; update Next.js to a patched release that bumps postcss >=8.5.10 (or add an npm override for postcss). Re-run npm audit to confirm 0 remaining, and smoke-test the build. | Fixed | package.json: bumped next 16.2.9->16.2.10, eslint-config-next to match, added overrides {postcss: ^8.5.16}. npm install resolved postcss 8.4.31->8.5.16. VERIFIED 2026-07-06: 'npm audit' now reports 0 vulnerabilities (was 2 moderate). Regression: 'next build' completes successfully (all routes compiled, exit 0), which also re-validates BUG-005/006 code changes. Note: restart the running dev server to pick up new node_modules.
BUG-009 | Weak password policy (minimum 6 characters, no complexity/breach checks) | Authentication & Session Management | Medium | app/login/actions.ts:47 (signup) and :92 (adminSignup) | Signup only enforces password.length >= 6 with no complexity, length ceiling, or breached-password check. Weak/reused passwords make member accounts — and especially admin accounts (BUG-001) — susceptible to credential stuffing and brute force. Supabase provides some login throttling but 6-char minimums are far below current guidance. | Raise the minimum to >=12 characters and enable Supabase Auth's leaked-password protection (HaveIBeenPwned) and minimum-strength settings. Enforce on both signup and password-change flows. Consider MFA for admin accounts. | Fixed | Raised minimum password length 6->12 in all three enforcement points: app/login/actions.ts (signup + adminSignup) and app/(app)/settings/actions.ts (change password); updated SettingsPassword.tsx placeholder. VERIFIED 2026-07-06: grep confirms no remaining '6 characters'/min-6 checks; tsc passes; production build passed (BUG-008). Regression: passwords >=12 still accepted, only <12 rejected. RECOMMENDED (dashboard, not code): enable Supabase Auth leaked-password protection (HaveIBeenPwned) + require MFA for admin accounts.
BUG-010 | Member email addresses over-fetched to all authenticated users (directory over-exposure) | API & Client-Server Trust (over-fetching) | Low | supabase/setup_profiles_auth.sql:36-37 (profiles readable by all authenticated); directory/list queries selecting email | Even after restricting anon access (BUG-002), the profiles policy lets ANY logged-in member read every other member's email column. A single logged-in account can scrape the entire membership's emails for spam/phishing. Email is not needed for the directory UI. | Do not expose email in directory/listing reads. Either drop email from the SELECT column lists and RLS-visible surface for non-owners, or move email behind an owner/admin-only view or RPC. Show contact only via in-app messaging. | Open (partially mitigated) | MITIGATED 2026-07-06: lib/profiles.ts getFullProfile() now nulls `email` for anyone but the profile owner, so scholar/other-profile pages no longer ship member emails to the client (own email still comes from the auth session). tsc passes. RESIDUAL: a logged-in member can still hand-craft GET /rest/v1/profiles?select=email to scrape emails, because profiles_select grants row SELECT to authenticated and email lives on that table. FULL FIX (deferred - core-path risk): remove email from the profiles table read path (revoke column SELECT from anon/authenticated), refactor getFullProfile to select explicit columns instead of select('*'), and serve the owner's own email from auth.users. Anon scraping is already blocked by BUG-002.
BUG-011 | Verbose authentication error messages returned to the client | Configuration & Secrets (verbose errors) | Low | app/login/actions.ts (login/signup return raw Supabase error.message) | Login and signup surface the raw Supabase error.message to the browser. Distinct messages (e.g. invalid credentials vs. unconfirmed email vs. rate-limited) can aid account enumeration and reconnaissance. | Return a single generic message for auth failures (e.g. 'Invalid email or password.'). Log the detailed error server-side only. Keep distinct messaging only for non-sensitive validation (empty field). | Fixed | app/login/actions.ts login(): auth failures now log the detailed Supabase error server-side and return a single generic 'Invalid email or password.', removing the invalid-user/unconfirmed/rate-limited oracle used for account enumeration. tsc passes. Signup's 'email already in use' left intact by design (standard signup UX, not a credential oracle).
BUG-012 | get_enum_values() granted to anon (schema/enum information disclosure) | API & Client-Server Trust | Low | supabase/phase1_writes.sql:16-28 (grant get_enum_values to anon) | get_enum_values(text) is executable by anon and returns the labels of any enum type in the database, letting an unauthenticated caller enumerate internal enum definitions (roles, degree levels, etc.). Minor information disclosure that aids mapping the schema. | Restrict the grant to 'authenticated' only (revoke from anon). The dropdown-building use case is only needed after login. | Fixed | Repo: phase1_writes.sql revokes get_enum_values from public/anon, grants to authenticated only; applied live via security_hardening.sql. VERIFIED LIVE 2026-07-06: anon rpc/get_enum_values now returns HTTP 401 'permission denied for function' (baseline returned ['scholar','alumni','admin']). Regression re-sweep same session: profiles/alumni_details anon reads still [], default admin code still 401 — no earlier fix regressed.